## Taska
Project | Start Date | End Date | Duration
Conduct a comprehensive assessment of current sesame seed supply chain disruptions (import restrictions, financial constraints) | 2025-01-01 | 2025-01-12 | 11 | 45658
Conduct a comprehensive assessment of the local sesame seed market, identifying potential suppliers and their capabilities | 2025-01-02 | 2025-01-12 | 10 | 45873
Analyze the impact of supply disruptions on production capacity and product availability | 2025-01-13 | 2025-01-19 | 6
Evaluate the quality standards of local sesame seed suppliers to ensure they meet company requirements | 2025-01-20 | 2025-01-26 | 6
Assess the financial viability of sourcing sesame seeds from local suppliers, including pricing and payment terms | 2025-01-27 | 2025-02-02 | 6
Establish initial contact with potential local suppliers and schedule meetings or site visits | 2025-02-03 | 2025-02-09 | 6
Identify and evaluate potential alternative suppliers of sesame seeds (domestic & international) | 2025-02-03 | 2025-02-16 | 13
Explore options for diversifying the supply chain to reduce reliance on a single source | 2025-02-17 | 2025-02-23 | 6
Negotiate favorable terms with suppliers (pricing, delivery schedules, flexible payment terms, long-term contracts) | 2025-02-24 | 2025-03-06 | 10
Develop long-term partnerships with reliable suppliers to ensure a consistent supply of sesame seeds | 2025-03-09 | 2025-03-13 | 4
Develop a financial plan to address increased costs associated with sesame seed sourcing | 2025-03-16 | 2025-03-25 | 9
Explore options for securing financing to cover upfront payments and operational costs | 2025-03-20 | 2025-04-03 | 14
Implement cost-saving measures to mitigate the financial impact of supply chain disruptions | 2025-04-06 | 2025-04-13 | 7
Develop and implement a rigorous quality control process for incoming sesame seeds | 2025-04-14 | 2025-04-27 | 13
Conduct regular inspections and testing to ensure compliance with quality standards | 2025-04-28 | 2025-05-11 | 13
Establish a system for tracking and managing quality issues | 2025-05-12 | 2025-05-18 | 6
Review and optimize production processes to accommodate the use of local sesame seeds | 2025-05-19 | 2025-05-29 | 10
Implement inventory management strategies to ensure optimal stock levels of sesame seeds and finished products | 2025-06-01 | 2025-06-12 | 11
Communicate transparently with customers about challenges and potential product availability issues | 2025-06-15 | 2025-06-19 | 4
Implement strategies to maintain customer loyalty and satisfaction during periods of supply shortages | 2025-06-22 | 2025-06-29 | 7
Develop a long-term customer relationship management plan to build trust and loyalty | 2025-07-01 | 2025-07-10 | 9
Continuously monitor the performance of local suppliers and the quality of sesame seeds | 2025-07-13 | 2025-07-27 | 14
Evaluate the impact of the new sourcing strategy on production costs, product quality, and overall operations | 2025-07-28 | 2025-08-04 | 7