## Used abbreviation
Used Abbreviations
Abbreviation | Word
O | Opportunity
T | Threat
H | High
M | Medium
Used Terms
Term | Definition
Risk | an uncertain event or condition that, if it occurs, has a positive or negative effect on a project's objectives
Risk ID | a risk statement based on feedback about causes, effects, impacts, areas of risk, and events.
Categories | specific elements within a project or its operational environment that could go wrong during the planning, implementation, or follow-up phases of an activity.
Probability | the determination of the likelihood of a risk occurring
Probability rate | the chance that a certain event may occur during the course of a project
Impact | an estimate of the potential losses associated with an identified risk.
Impact rate | the estimation of the severity of a risk's consequences. Risk impacts can range from catastrophic to inconsequentia
Response strategy | an action plan on what you will do a Risk on your project
Action items | a task or activity that needs to get done to survive the threats or capitalize on opportunities
Watchlist | where low priority risks are tracked.
Trigger | a indicator that a risk is about to occur or has occurred.

## Dashboard
Risk Matrix
|  |  |  | Low | Medium | High
|  |  | Probability | 3 | 6 | 9
|  | High | 9 |  |  | T1
|  | Medium | 6 |  |  | T2, T9
|  | Low | 3 | T5 | T6, T7, T8 | T3, T4
Impact
|  |  |  | Low | Medium | High
|  |  | High | Medium | Low
Category | Marketing | Sales | Financial | Operational
Total | 1 | 2 | 2 | 4
Probability | High | Medium | Low
Total | 1 | 2 | 6

## Risk list
No. | Risk | T/O | Risk ID | Category | Probability | Probability rate | Impact | Impact rate | Risk rate PR*IR | Response strategy | Action items | Watchlist | Trigger
1 | Inflation that affects the prices | T | T1 | Finance | H | 9 | H | 9 | 81 | Accept | Implement a price adjustment clause in contracts to accommodate for inflationary changes. | No | A sudden increase in the inflation rate above 5% over a quarter.
2 | Supplier have more privilige in negotiations | T | T2 | Operational | M | 6 | H | 9 | 54 | Mitigate | Diversify supplier base to reduce over-reliance on a single supplier. | No | Supplier changes contract terms significantly in their favor (e.g., price increases, quantity constraints).
3 | Supplier delay the sesame supply | T | T3 | Operational | L | 3 | H | 9 | 27 | Avoid | Set up buffer stocks and backup suppliers to ensure continuous supply. | No | A delay of more than one week beyond agreed delivery dates.
4 | The supply not suffecient for the production | T | T4 | Operational | L | 9 | H | 9 | 81 | Mitigate | Implement detailed forecasting and stock management tools. | No | Inventory levels drop below the minimum stock threshold for production.
5 | The Quality not as required | T | T5 | Operational | L | 3 | L | 3 | 9 | Avoid | Implement stricter quality control and inspection measures upon receiving goods. | Yes | Three consecutive batches failing quality standards.
6 | The new production with local supplier doesn't meet customer preferences | T | T6 | Marketing | L | 3 | M | 6 | 18 | Avoid | Conduct pilot testing with target customers before mass production. | No | A decline in customer satisfaction metrics by 10% or more.
7 | Customers may switch to other brands if they perceive a change in taste | T | T7 | Sales | L | 3 | M | 6 | 18 | Mitigate | Maintain consistent quality and conduct regular taste tests with loyal customers. | No | A significant increase in customer complaints regarding taste, or a drop in sales of 5% or more.
8 | Supplier may expand and start his own Tahini production line | T | T8 | Sales | L | 3 | M | 6 | 18 | Avoid | Develop long-term exclusive supply agreements to prevent competition. | No | Supplier announces expansion plans that could compete with Halwani’s tahini production.
9 | Changes in payment terms or reliance on a single supplier lead to tighter cash flow management. | T | T9 | Finance | M | 6 | H | 9 | 54 | Mitigate | Negotiate flexible payment terms and seek alternative financing solutions. | No | Supplier demands shorter payment terms or significantly higher upfront payments.