## Projects
Item | Pro Leaders - DM Agencies | Al Anwarr - Customized Furniture | Al Anwarr - Smart Furniture | TalkyBot | Pro Leaders - Current Situation High Level
Current Situation Analysis
Delivert Date |  | 2021-05-17
Owner |  | Mr. Mostafa
Questionnair
Delivert Date | 2021-06-03
Owner | Khloud
Industry Report
Delivert Date | 2021-06-03 | 2021-06-03 | 2021-07-04 | 2021-08-29
Owner | Khloud & Rana | Ms. Heba | Ms. Heba | Khloud
Marketing Plan
Delivert Date | 2021-06-17 | 2021-06-17 | 2021-08-29 | 2021-09-12
Owner | Khloud | Ms. Heba | Ms. Heba | Khloud
Sales Plan
Delivert Date | 2021-06-24 |  |  | 2021-09-19
Owner | Khloud |  |  | Khloud
Operational Plan
Delivert Date | 2021-08-22 |  |  | 2021-09-26
Owner | Mr. Mostafa |  |  | Mr. Mostafa
Financial Modeling
Delivert Date | 2021-09-02 |  | 2021-09-12 | 2021-10-31
Owner | Rana |  | Rana | Rana
Risk Management Plan
Delivert Date | 2021-09-09 |  |  | 2021-10-03
Owner | Khloud |  |  | Khloud
Exit & Expansion Scenarios
Delivert Date | 2021-09-16 |  |  | 2021-10-10
Owner | Khloud |  |  | Rana

## Owners
Project | Owner | Start Date | End Date | Duration
Customize Furniture - Current Situation Analysis | Mr. Mostafa | 2021-05-06 | 2021-05-17 | 11
Customize Furniture - Industry Report | Ms. Heba | 2021-05-17 | 2021-06-03 | 17
Customize Furniture - Marketing Plan | Ms. Heba | 2021-06-06 | 2021-06-17 | 11
Smart Furniture - Industry Report | Ms. Heba | 2021-06-20 | 2021-07-04 | 14
Smart Furniture - Marketing Plan | Ms. Heba | 2021-07-05 | 2021-07-08 | 3
Furniture - Financial Modeling | Rana | 2021-07-11 | 2021-07-29 | 18
Pro-Leaders, DM Agencies - Questionnaire | Khloud | 2021-05-17 | 2021-05-27 | 10
Pro-Leaders, DM Agencies - Industry Report | Khloud | 2021-05-17 | 2021-06-03 | 17
Pro-Leaders, DM Agencies - Industry Report | Rana | 2021-05-17 | 2021-06-03 | 17
Pro-Leaders, DM Agencies - Marketing Plan | Khloud | 2021-06-06 | 2021-06-17 | 11
Pro-Leaders, DM Agencies - Sales Plan | Khloud | 2021-06-20 | 2021-06-24 | 4
Pro-Leaders, DM Agencies - Operational Plan | Mr. Mostafa | 2021-06-27 | 2021-07-04 | 7
Pro-Leaders, DM Agencies - Financial Modeling | Rana | 2021-07-05 | 2021-07-29 | 24
Pro-Leaders, DM Agencies - Risk Management Plan | Khloud | 2021-07-08 | 2021-07-15 | 7
Pro-Leaders, DM Agencies - Exit & Expansion Scenarios | Khloud | 2021-07-11 | 2021-07-15 | 4

## Projects' Timeline
Project | Task | Filter by? | Start Date | End Date | Duration
Digital Marketing Agency | DM - Operational Plan | Operational Plan | 2021-09-12 | 2021-09-19 | 7
Digital Marketing Agency | DM - Risk Management | Risk Management | 2021-09-20 | 2021-09-27 | 7
Digital Marketing Agency | DM - Exit & Expansion | Exit & Expansion | 2021-09-20 | 2021-09-27 | 7
Digital Marketing Agency | DM - Financial Modeling | Financial Modeling | 2021-09-29 | 2021-10-13 | 14
Talkybot | Talkybot - Industry Report | Industry Report | 2021-08-18 | 2021-09-23 | 36
Talkybot | Talkybot - Marketing Plan | Marketing Plan | 2021-10-03 | 2021-10-17 | 14
Talkybot | Talkybot - Sales Plan | Sales Plan | 2021-10-19 | 2021-10-26 | 7
Talkybot | Talkybot - Operational Plan | Operational Plan | 2021-10-31 | 2021-11-07 | 7
Talkybot | Talkybot - Risk Management | Risk Management | 2021-11-10 | 2021-11-17 | 7
Talkybot | Talkybot - Exit & Expansion | Exit & Expansion | 2021-11-21 | 2021-11-28 | 7
Talkybot | Talkybot - Financial Modeling | Financial Modeling | 2021-12-01 | 2021-12-15 | 14
HomeXet | HomeXat - Industry Report | Industry Report | 2021-09-01 | 2021-10-12 | 41
HomeXet | HomeXat - Marketing Plan | Marketing Plan | 2021-10-17 | 2021-10-31 | 14
HomeXet | HomeXat - Sales Plan | Sales Plan | 2021-11-01 | 2021-11-08 | 7
HomeXet | HomeXat - Operational Plan | Operational Plan | 2021-11-10 | 2021-11-17 | 7
HomeXet | HomeXat - Risk Management | Risk Management | 2021-11-21 | 2021-11-28 | 7
HomeXet | HomeXat - Exit & Expansion | Exit & Expansion | 2021-11-21 | 2021-11-28 | 7
HomeXet | HomeXat - Financial Modeling | Financial Modeling | 2021-12-02 | 2021-12-19 | 17
Customized & Smart Furniture | Furniture - Financial Modeling | Financial Modeling | 2021-09-27 | 2021-10-12 | 15
Ra7tak | Ra7tak - Industry Report | Industry Report | 2021-09-06 | 2021-10-18 | 42
Ra7tak | Ra7tak - Marketing Plan | Marketing Plan | 2021-10-20 | 2021-11-03 | 14
Ra7tak | Ra7tak - Sales Plan | Sales Plan | 2021-11-07 | 2021-11-14 | 7
Ra7tak | Ra7tak - Operational Plan | Operational Plan | 2021-11-16 | 2021-11-23 | 7
Ra7tak | Ra7tak - Risk Management | Risk Management | 2021-11-25 | 2021-12-02 | 7
Ra7tak | Ra7tak - Exit & Expansion | Exit & Expansion | 2021-12-05 | 2021-12-12 | 7
Ra7tak | Ra7tak - Financial Modeling | Financial Modeling | 2021-12-14 | 2021-12-28 | 14
Realestate app commission | Realestate - Industry Report | Industry Report | 2021-09-14 | 2021-10-27 | 43
Realestate app commission | Realestate - Marketing Plan | Marketing Plan | 2021-10-31 | 2021-11-14 | 14
Realestate app commission | Realestate - Sales Plan | Sales Plan | 2021-11-16 | 2021-11-23 | 7
Realestate app commission | Realestate - Operational Plan | Operational Plan | 2021-11-28 | 2021-12-05 | 7
Realestate app commission | Realestate - Risk Management | Risk Management | 2021-12-07 | 2021-12-14 | 7
Realestate app commission | Realestate - Exit & Expansion | Exit & Expansion | 2021-12-19 | 2021-12-26 | 7
Realestate app commission | Realestate - Financial Modeling | Financial Modeling | 2021-12-29 | 2022-01-13 | 15
EV feasibility study | EV - Feasibility Study | Feasibility Study | 2021-09-19 | 2021-10-11 | 22