## Projects
Item | Pro Leaders - DM Agencies | Al Anwarr - Customized Furniture | Al Anwarr - Smart Furniture
Current Situation Analysis
Delivert Date |  | 2021-05-17
Owner |  | Mr. Mostafa
Questionnair
Delivert Date | 2021-05-23
Owner | Khloud
Industry Report
Delivert Date | 2021-06-06 | 2021-06-07 | 2021-07-05
Owner | Khloud & Rana | Ms. Heba | Ms. Heba
Marketing Plan
Delivert Date | 2021-06-20 | 2021-06-21 | 2021-07-12
Owner | Khloud | Ms. Heba | Ms. Heba
Sales Plan
Delivert Date | 2021-06-27
Owner | Khloud
Operational Plan
Delivert Date | 2021-07-04
Owner | Mr. Mostafa
Financial Modeling
Delivert Date | 2021-07-18 | 2021-07-26 | 2021-07-26
Owner | Rana | Rana | Rana
Risk Management Plan
Delivert Date | 2021-07-18
Owner | Khloud
Exit & Expansion Scenarios
Delivert Date | 2021-07-25
Owner | Khloud

## Owners
Project | Owner | Start Date | End Date | Duration
Customize Furniture - Current Situation Analysis | Mr. Mostafa | 2021-05-06 | 2021-05-17 | 11
Customize Furniture - Industry Report | Ms. Heba | 2021-05-18 | 2021-06-07 | 20
Customize Furniture - Marketing Plan | Ms. Heba | 2021-06-08 | 2021-06-21 | 13
Smart Furniture - Industry Report | Ms. Heba | 2021-06-22 | 2021-07-05 | 13
Smart Furniture - Marketing Plan | Ms. Heba | 2021-07-06 | 2021-07-12 | 6
Furniture - Financial Modeling | Rana | 2021-07-13 | 2021-07-26 | 13
Pro-Leaders, DM Agencies - Questionnaire | Khloud | 2021-05-17 | 2021-05-23 | 6
Pro-Leaders, DM Agencies - Industry Report | Khloud | 2021-05-17 | 2021-06-06 | 20
Pro-Leaders, DM Agencies - Industry Report | Rana | 2021-05-17 | 2021-06-06 | 20
Pro-Leaders, DM Agencies - Marketing Plan | Khloud | 2021-06-07 | 2021-06-20 | 13
Pro-Leaders, DM Agencies - Sales Plan | Khloud | 2021-06-21 | 2021-06-27 | 6
Pro-Leaders, DM Agencies - Operational Plan | Mr. Mostafa | 2021-06-28 | 2021-07-04 | 6
Pro-Leaders, DM Agencies - Financial Modeling | Rana | 2021-07-05 | 2021-07-18 | 13
Pro-Leaders, DM Agencies - Risk Management Plan | Khloud | 2021-07-12 | 2021-07-18 | 6
Pro-Leaders, DM Agencies - Exit & Expansion Scenarios | Khloud | 2021-07-19 | 2021-07-25 | 6